## Pay-Cirteficate (hidden)
[5 empty] | Total no. of pages |  |  |  | A2 | E1 | E2
[5 empty] | Contract № |  |  |  | 1919685.5 | 2017411.895 | 1264301.3752
Date of Signature of Contract:
[5 empty] | Date: | 2023-05-09
| Payment Certificate № |  |  | 1 to 5
| PROJECT: | Construction of Apartment Buildings (E-1 & - ) |  |  |  |  | E1+E1 | 4034823.7899
LOCATION: |  | Addis Ababa, Jemmo II Site |  |  |  |  | E1+E2 | 3281713.2702
CLIENT: |  | Nifasilk Lafto Sub-City H/D/P/Office |  |  |  |  | E2+A2 | 3183986.8752
CONSULTANT: |  | MGM Consult PLC |  |  |  | AMOUNT (Birr) | A2+A2 | 3839371
| CONTRACTOR: |  |  |  | Main Cont. |  | E2+E2 | 2528602.7505
| Adress | Addis Ababa |  |  | Additional Cont.
| Telephone |  |  |  | Variation Order No.
| P.O. Box |  |  |  | Sub Total | 0
[5 empty] | VAT 15% | 0
| As per the attached statement the value of work executed and/or materials supplied todate is: |  |  |  | Total Sum | 0
#REF!
|  |  |  | (a)---------------------------------------------------------------------- |  | Amount (Birr)
Previous Payments | [5 empty] | #REF!
Item No. | Date | Amount (Birr) Before VAT | VAT |  | Amount (Birr)
AD1 |  |  |  | Previous Payment | 0
AD2 |  |  |  | Rebate |  |  | 1 | 2 | 3 | 4
AD3 |  |  |  | (b)-------------------------- Retention (5%) | #REF! |  | 18591.84 | 25680.24 | 32664.12 | 39565.72
1 |  |  |  | Penalty
2 |  |  |  | (c)-----------Advance Repayment (20%) | #REF!
3
4 |  |  |  | Total | #REF! | #REF!
5 |  |  |  | Net sum due to the contractor |  | #REF!
6 |  |  |  | (d) =15%*((a) - (c)) ----------------------- | 15% VAT | #REF!
7 |  |  |  |  | Previous VAT 15% | 0
8 |  |  |  |  | Net 15% VAT | #REF! | #REF!
TOTAL |  | 0 | 0 | We here by certify that the contractor is now entitled to the sum of Birr = |  | #REF!
In words
Prepared By: -
(Signature)
| Approved |  |  | Authorized
|  | (Signature) |  |  | (Signature)

## Block Summary (hidden)
Contructor: -
Consultant: - MGM Consult PLC
| Payment №: | 1 to 5
| Date: | 2023-05-09
GRAND SUMMARY
| Typology | Unit | Amount
1 | Block Type E-1 (200Kpa) | Birr | #REF!
2 | Block Type E-2 (200Kpa) | Birr
3 | Block Type A-2 (200Kpa) | Birr
| GRAND TOTAL ........................................ | Birr | #REF!
Contractor
Site Inspector
Qty. Surveyor
Resident Eng.
Project Coordinator

## BOQ
BILL OF QUANTITIES
FOR
ST. LUKAS HOSPITAL EXTERNAL FENCE
1 | Excavation and Earth Work……………………………………….…………………… | Birr
2 | Concrete Work………………………………………………………………………………… | Birr
3 | Masonary Works…………………………………………………...……….………………………… | Birr
4 | Block Works…………………………………………………...……….………………………… | Birr
5 | Metal and Related Works…………………………………………………...……….………………………… | Birr
6 | Finishing Works…………………………………………………...……….………………………… | Birr
| Total ................... | Birr
| VAT (15%)…............... | Birr
| Grand Total ................... | Birr
Item No | Description | Unit | Qty | Unit Rate | Amount
1.0 EXCAVATION & EARTH WORK
1.01 | Clear and remove top soil to an average depth of 200mm. The site clearance shall include removing existing fence, cutting & up rooting of bushes of tree on the site. | M2 | 234
1.02 | Trench Excavation for masonry foundation wall to a depth not exceeding 100cm from reduced ground level | M3 | 312
1.03 | Pit excavation in ordinary soil to reduce level to depth not exceeding 1500mm . | M3 | 158.4
1.04 | Back Fill under Massonary foundation with imported selected material from quarry waste well rolled and compacted in layers not exceeding 200 mm thick. | M3 | 267.66
1.05 | Load and cart away surplus excavated material to an appropriate tip not exceeding 5km from the site. | M3 | 517.2
TOTAL CARRIED TO SUMMARY ...................................................
2.0 CONCRETE WORK
2.01 | 50 mm lean concrete quality C-5, with minimum cement content of 150 kg /m3, of concrete:
| a) Under Masonary Foundation | M2 | 159
| b) Under Footing Pad | M2 | 81
2.02 | Reinforced concrete quality C-25,360 kg of cement/m3 filled in to form work and vibrated around rod reinforcement (Formwork and reinforcement measured separately)
| a) In Grade Beam [30cm x 50cm] | M3 | 58.5
| b) In Collumn Footing Pad | M3 | 43.74
| c) In Main Collumn [30cm x 30cm] | M3 | 5.832
| d) In Intermidiate Collumn [20cm x 20cm ] | M3 | 5.472
2.03 | Provide, cut and fix in position sawn structural wood or steel formwork which ever is appropriate. | [5 empty] | 114
| a) In Grade Beam [30cm x 50cm] | M3 | 234
| b) In Collumn Footing Pad | M3 | 151.2
| c) In Main Collumn [30cm x 30cm] | M3 | 5.832
| d) In Intermidiate Collumn [20cm x 20cm ] | M3 | 5.472
2.04 | Mild steel reinforcement according to structural drawings. Price includes cutting, bending, placing in position, tying wire, concrete spacers and reinforcement bar chairs.
| a) Dia. 08 mm deformed bar | Kg | 1626.02
| b) Dia. 12 mm deformed bar | Kg | 3004.99
| c) Dia. 14mm deformed bar | Kg | 1820.81
TOTAL CARRIED TO SUMMARY ...................................................
3. MASONARY WORK
3.01 | 500mm thick at top and 80 cm thick at bottom hard trachytic roughly dressed stone masonry retaining wall bedded in cement mortar mix ratio (1:3)
| a) By reusing existing massonary stone after cleaning [Provisional] | M3 | 123.24 |  |  | 10
| b) By using new massonary stone suplied by contractor [Provisional] | M3 | 123.24
3.02 | Ditto but for exposed part above natural ground level.
| a) By reusing existing massonary stone after cleaning [Provisional] | M3 | 61.62
| b) By using new massonary stone suplied by contractor [Provisional] | M3 | 61.62
TOTAL CARRIED TO SUMMARY ...................................................
4. BLOCK WORKS
4.01 | Class C, 200mm thick HCB wall which can satisfy the designed strength , bedded in cement mortar (1:3).Price shall include mortar beding.
| a) [20 cm x 20 cm x 40 cm] | M2 | 352.8
TOTAL CARRIED TO SUMMARY ...................................................
5. METAL WORK
5.01 | All metal RHS Iron frames shown on the drawings, All metal works shall be painted one coat primer and 3 coats of synthetic enamel paint. The dimension and spacing of steel members shoild be chacked from the drawing.
| a) RHS 40*40, 3.0 mm thick Vertical Support member | Kg | 1032.95
| b) RHS 40*400, 3.0 mm thick Lateral members | Kg | 1271.33
5.02 | All metal RHS Iron frames shown on the drawings, All metal works shall be painted one coat primer and 3 coats of synthetic enamel paint. The dimension and spacing of steel members shoild be chacked from the drawing.
| a) Dismantling and reinstallation of existing gate after properly fixing it to meet the desired standard and approved by the Engineer In-Charge | Pc | 2
TOTAL CARRIED TO SUMMARY ...................................................
6. FINISHING WORK
6.01 | Apply three coats of plastering in cement mortar (1:3) to all internal walls, 5cm width outer edge of doors & windows, exposed surface of beams and column up to fine finish. Price shall include Pre-cleaning, preparation of the surface and all edge works.
| a) To internal & external HCB wall (Price shall include capping with concrete) | M2 | 705.6
| b) To exposed column and beams (Price shall include Edge finishing works) | M2 | 150
6.02 | Apply pointing to exposed part above ground level stone masonry foundation wall recessed joint in cement sand mortar mix (1:2). (PROVSIONAL)
M2
6.03 | Apply three coats of plastic emulsion paint. Price shall include pre - cleaning & preparation of the surface.
| a) To internal & external HCB wall | M2 | 705.6
| b) To exposed column and beams | M2 | 150
TOTAL CARRIED TO SUMMARY ...................................................
TOTAL SUMMARY

## Takoff Sheet
Project :- | St. Lukas Hospital External Fence |  |  |  | Contractor:- To Be Assigned
Client:- Doctors With Africa CUAMM |  |  |  |  | Location :-Woliso Town, Oromia, Ethiopia
Takeoff sheet
Item |  |  | Dimension | Qty | Description
A- SUB STRUCTURE
1.00 Excavation & Earth Work
[5 empty] | 1.01 | Site Clearance
1 | 1 | 1 | 390 |  |  | Length = 390.00 meter
|  |  | 0.6 | 234 |  | Width = 0.60 meter
|  |  |  | 234 | (Total to Item 1.01)
[5 empty] | 1.02 | Trench Excavation
1 | 1 | 1 | 390 |  |  | Length = 390.00 meter
|  |  | 0.8 |  |  | Width = 0.80 meter
|  |  | 1 | 312 |  | Depth = 1.00 meter
|  |  |  | 312 | (Total to Item 1.02)
[5 empty] | 1.03 | Pit Excavation
1 | 1 | 36 | 2 |  |  | Length = 1.50 + 0.25 *+ 0.25 = 2.00 meter
|  |  | 2 |  |  | Width = 1.50 + 0.25 *+ 0.25 = 2.00 meter
|  |  | 1.5 | 216 |  | Depth = 1.50 meter (Expected footing Qty is 36) |  | 54
Deductable
-1 | 1 | 1 | 72 |  |  | Excavated volume of trench
|  |  | 0.8 |  |  | Length = 36 * 2.00 = 72.00 meter
|  |  | 1 | -57.6 |  | Width = 0.80 meter, Depth = 1.00 meter
|  |  |  | 158.4 | (Total to Item 1.03)
[5 empty] | 1.04 | Back fill
Around Stone Massonary
1 | 1 | 1 | 318 |  |  | Length = 390.00 - (36 * 2 .00) = 318.00 meter
|  |  | 0.3 |  |  | Width = 0.30 meter
|  |  | 1 | 95.4 |  | Depth = 1.00 meter
Around Foundation Footing
1 | 1 | 36 | 2 |  |  | Length = 1.50 + 0.25 *+ 0.25 = 2.00 meter
|  |  | 2 |  |  | Width = 1.50 + 0.25 *+ 0.25 = 2.00 meter
|  |  | 1.5 | 216 |  | Depth = 1.50 meter (Expected footing Qty is 36)
Deductable
|  |  |  | -43.74 |  | Concrete Volume = (36*1.215)= 43.74 M3
|  |  |  | 267.66 | (Total to Item 1.04)
[5 empty] | 1.05 | Cart Away
1 | 1 | 1 | 78 | 517.2 |  | Total excavated voume.
|  |  |  | 517.2 | (Total to Item 1.05)
2.0 Concrete Work
[5 empty] | 2.01 | C-5 Lean concrete
[5 empty] | 2.01 a) | Under masonry
1 | 1 | 1 | 318 |  |  | Length = 390.00 - (36 * 2 .00) = 318.00 meter
|  |  | 0.5 | 159 |  | Width = 0.50 meter
|  |  |  | 159 | (Total to Item 2.01a)
[5 empty] | 2.01 a) | Under Footing Pad
1 | 1 | 36 | 1.5 |  |  | Length = 1.50 meter
|  |  | 1.5 | 81 |  | Width = 1.50 meter
|  |  |  | 81 | (Total to Item 2.01a)
[5 empty] | 2.02 | C-25 Concrete
[5 empty] | 2.02 a) | In Grade Beam [30cm x 50cm]
1 | 1 | 1 | 390 |  |  | Length = 390 meter
|  |  | 0.5 |  |  | Width = 0.5 meter, Depth = 0.30 meter
|  |  | 0.3 | 58.5
|  |  |  | 58.5 | (Total to Item 2.02a)
[5 empty] | 2.02 b) | In Elevation Collumn & Footing Pad
Footing Pad
1 | 1 | 36 | 1.5 |  |  | Length = 1.50 meter
|  |  | 1.5 |  |  | Width = 1.50 meter, Depth = 1.50 meter
|  |  | 0.5 | 40.5
[6 empty] | Elevation Collumn |  |  | 27.8571
1 | 1 | 36 | 0.3 |  |  | Length = 0.30 meter
|  |  | 0.3 |  |  | Width = 0.30 meter, Depth = 1.00 meter
|  |  | 1 | 3.24
|  |  |  | 43.74 | (Total to Item 2.02b)
[5 empty] | 2.02 c) | In Main Collumn [30cm x 30cm]
1 | 1 | 36 | 0.3 |  |  | Length = 1.80 meter
|  |  | 0.3 |  |  | Width = 0.30 meter, Depth = 0.30 meter
|  |  | 1.8 | 5.832
|  |  |  | 5.832 | (Total to Item 2.02c) |  |  |  | 111.4286
[5 empty] | 2.02 d) | In Intermidiate Collumn [20cm x 20cm ] |  |  | 76
1 | 1 | 76 | 0.2 |  |  | Length = 1.80 meter
|  |  | 0.2 |  |  | Width = 0.20 meter, Depth = 0.20 meter
|  |  | 1.8 | 5.472 |  | Estimated 76 Intermidiate column
|  |  |  | 5.472 | (Total to Item 2.02cd)
[5 empty] | 2.03 | Formwork
[5 empty] | 2.03 a) | In Grade Beam [30cm x 50cm]
1 | 1 | 2 | 390 |  |  | Length = 390 meter
|  |  | 0.3 | 234 |  | Width = 0.3 meter
|  |  |  | 234 | (Total to Item 2.03a)
[5 empty] | 2.03 b) | In Elevation Collumn & Footing Pad
Footing Pad
1 | 36 | 4 | 1.5 |  |  | Length = 1.50 meter
|  |  | 0.5 | 108 |  | Width = 0.50 meter
[6 empty] | Elevation Collumn |  |  | 27.8571
1 | 36 | 4 | 0.3 |  |  | Length = 1.00 meter
|  |  | 1 | 43.2 |  | Width = 0.30 meter
|  |  |  | 151.2 | (Total to Item 2.03b)
[5 empty] | 2.03 c) | In Main Collumn [30cm x 30cm]
1 | 1 | 36 | 0.3 |  |  | Length = 1.80 meter
|  |  | 0.3 |  |  | Width = 0.30 meter, Depth = 0.30 meter
|  |  | 1.8 | 5.832
|  |  |  | 5.832 | (Total to Item 2.03c) |  |  |  | 111.4286
[5 empty] | 2.03 d) | In Intermidiate Collumn [20cm x 20cm ] |  |  | 76
1 | 1 | 76 | 0.2 |  |  | Length = 1.80 meter
|  |  | 0.2 |  |  | Width = 0.20 meter, Depth = 0.20 meter
|  |  | 1.8 | 5.472 |  | Estimated 76 Intermidiate column
|  |  |  | 5.472 | (Total to Item 2.03d)
[5 empty] | 2.04 | Mild steel reinforcement
2.04 a) Dia. 08 mm deformed bar
1 | 1 | 1 | 1626.0175 | 1626.0175
|  |  |  | 1626.02 | (Total to Item 2.04 a)
2.04 b) Dia. 12 mm deformed bar
1 | 1 | 1 | 3004.992 | 3004.992
|  |  |  | 3004.99 | (Total to Item 2.04 b)
2.04 c) Dia. 14 mm deformed bar
1 | 1 | 1 | 1820.808 | 1820.808
|  |  |  | 1820.81 | (Total to Item 2.04 c)
3.0 Masonry Work
3.01 Below ground level
Vertical Section
1 | 1 | 1 | 379.2 |  |  | Length = 390 - 36(*0.3) = 379.20 meter
|  |  | 0.5 |  |  | Width = 0.50 meter
|  |  | 1 | 189.6 |  | Depth = 1.00 meter
Sloped Section
1 | 0.5 | 1 | 379.2 |  |  | Length = 390 - 36(*0.3) = 379.20 meter
|  |  | 0.3 |  |  | Width = 0.30 meter
|  |  | 1 | 56.88 |  | Depth = 1.00 meter
|  |  |  | 246.48 | (Total to Item 3.01)
3.02 Above Ground Level
Vertical Section
1 | 1 | 1 | 379.2 |  |  | Length = 390 - 36(*0.3) = 379.20 meter
|  |  | 0.5 |  |  | Width = 0.50 meter
|  |  | 0.5 | 94.8 |  | Depth = 1.00 meter
Sloped Section
1 | 0.5 | 1 | 379.2 |  |  | Length = 390 - 36(*0.3) = 379.20 meter
|  |  | 0.3 |  |  | Width = 0.30 meter
|  |  | 0.5 | 28.44 |  | Depth = 0.50 meter
|  |  |  | 123.24 | (Total to Item 3.02)
4.0 H.C.B Work
[5 empty] | 4.01 | Class -B 15*20*40 HCB
1 | 1 | 76 | 3.2 |  |  | Length = 3.20 meter
|  |  | 1.5 | 364.8 |  | Height = 1.50 meter | (Total of 76 Sections)
1 | 1 | 2 | 4 |  | Door
|  |  | 1.5 | 12 | DDT
|  |  |  | 352.8 | (Total to Item 4.01)
[5 empty] | 5 | METAL WORK
5.00 a) RHS 40*40, 3.0 mm thick Vertical Support member
1 | 38 | 0.6 | 13 |  |  | Length on one section = 0.6 * 13 = 7.80 meter
|  |  | 3.485 | 1032.954 |  | Wight per Meter =3.485 kg/m
|  |  |  | 1032.95 | (Total to Item 5.00 a)
5.01 b) RHS 40*40, 3.0 mm thick lateral Support member
1 | 38 | 3 | 3.2 |  |  | Length on one section = 3.20 * 3 = 9.60 meter
|  |  | 3.485 | 1271.328 |  | Wight per Meter =3.485 kg/m
|  |  |  | 1271.33 | (Total to Item 5.00 b)
5.02 Renovationg Existing door {Gate}
1 | 1 | 1 | 2 | 2 |  | Desmatle and reinstall existing gate after properly renovation it.
|  |  |  | 2 | (Total to Item 5.02)
6. FINISHING WORK
[5 empty] | 6.01 | a) Internal and External Wall of HCB
1 | 1 | 2 | 352.8 | 705.6
|  |  |  | 705.6 | (Total to Item 6.01a)
[5 empty] | 6.01 | b) To Exposed column and beams
1 | 1 | 1 | 150 | 150
|  |  |  | 150 | (Total to Item 6.01b)
[5 empty] | 6.02 | Painting
[5 empty] | 6.02 | a) Internal and External Wall of HCB
1 | 1 | 2 | 352.8 | 705.6
|  |  |  | 705.6 | (Total to Item 6.02a)
[5 empty] | 6.02 | b) To Exposed column and beams
1 | 1 | 1 | 150 | 150
|  |  |  | 150 | (Total to Item 6.02b)

## Re-Bar Schedule
Reinforcement Bar Schedule
Location | ф | Length (m) | No. of Bars | No. of Mem. | Length for ф
[5 empty] | 6 | 8 | 10 | 12 | 14 | 16
Footing Pad
L1 = 1.90 meter | 14 | 1.9 | 11 | 36 | - | - | - | - | 752.4 | -
L2 = 1.90 meter | 14 | 1.9 | 11 | 36 | - | - | - | - | 752.4 | -
Elevation Column
L1 = 3.50 meter | 12 | 3.5 | 6 | 36 | - | - | - | 756 | 0 | -
Stirrups | [11 empty] | 15
L1; L=1.05; N=(3.00/0.20)+1=16 | 8 | 1.05 | 16 | 36 | - | 604.8 | - | - | - | -
Interm Column
L1 = 2.00 meter | 12 | 2 | 4 | 36 | - | - | - | 288 | 0 | - | 10
Stirrups | [11 empty] | 15
L1; L=0.70; N=(2.0/0.20)+1=11 | 8 | 0.7 | 11 | 76 | - | 585.2 | - | - | - | -
Grade Beam
L1 = 390 meter | 12 | 390 | 3 | 1 | - | - | - | 1170 | 0 | -
L2 = 390 meter | 12 | 390 | 3 | 1 | - | - | - | 1170 | 0 | -
Stirrups | [10 empty] | 1950 | 15
L1; L=1.50; N=(390/0.20)+1=1951 | 8 | 1.5 | 1951 | 1 | - | 2926.5 | - | - | - | -
[5 empty] | - | - | - | - | - | -
[5 empty] | - | - | - | - | - | -
|  | Total Length |  |  | 0 | 4116.5 | 0 | 3384 | 1504.8 | 0
|  | Weight per m. |  |  | 0.222 | 0.395 | 0.617 | 0.888 | 1.21 | 0.888
|  | Total weight, kg. |  |  | 0 | 1626.0175 | 0 | 3004.992 | 1820.808 | 0

## RB E-1 Resi. Super St with 20mm (hidden)
Contractor: Consultant: MGM CONSULTING PLC | [6 empty] | Block № |  | Block Type | E-1 Resi | BC | 200 | Payment № |  | #REF!
№ | Location | Type | Dia | Length | Timizing |  |  | Total | 6 | 8 | 10 | 12 | 14 | 16 | 20
[5 empty] | Flr | Mbr | Rbr
0
| Elevation Column | [6 empty] | 0
| Ground Floor | [14 empty] | Ground Floor
| C-1 | Main Bar | 20 | 3.68 | 1 | 2 | 12 | 24 | [6 empty] | 88.32 | C-1 | Main Bar | 20 | 3.68 | 1 | 2 | 12
| Stirupe | a | 8 | 1.2 | 1 | 2 | 13 | 26 |  | 31.2 | [5 empty] | stirrup | a | 8 | 1.2 | 1 | 2 | 13 | 31.2
| C-2 | Main Bar | 20 | 3.68 | 1 | 2 | 8 | 16 | [6 empty] | 58.88 | C-2 | Main Bar | 20 | 3.68 | 1 | 2 | 8
| Stirupe | a | 8 | 1.2 | 1 | 2 | 13 | 26 |  | 31.2 | [5 empty] | stirrup | a | 8 | 1.2 | 1 | 2 | 13 | 31.2
| C-3 | Main Bar | 20 | 3.68 | 1 | 2 | 12 | 24 | [6 empty] | 88.32 | C-3 | Main Bar | 20 | 3.68 | 1 | 2 | 12
| b | b | 8 | 1.3 | 1 | 2 | 13 | 26 |  | 33.8 | [5 empty] | b | b | 8 | 1.3 | 1 | 2 | 13 | 33.8
| C-4 | Main Bar | 16 | 3.52 | 1 | 10 | 8 | 80 | [5 empty] | 281.6 |  | C-4 | Main Bar | 16 | 3.52 | 1 | 10 | 8
| Stirupe | a | 8 | 1.2 | 1 | 10 | 14 | 140 |  | 168 | [5 empty] | stirrup | a | 8 | 1.2 | 1 | 10 | 14 | 168
| C-5 | Main Bar | 20 | 3.68 | 1 | 2 | 8 | 16 | [6 empty] | 58.88 | C-5 | Main Bar | 20 | 3.68 | 1 | 2 | 8
| b | b | 8 | 1.3 | 1 | 2 | 13 | 26 |  | 33.8 | [5 empty] | b | b | 8 | 1.3 | 1 | 2 | 13 | 33.8
| C-6 | Main Bar | 20 | 3.68 | 1 | 2 | 8 | 16 | [6 empty] | 58.88 | C-6 | Main Bar | 20 | 3.68 | 1 | 2 | 8
| Stirupe | a | 8 | 1.2 | 1 | 2 | 13 | 26 |  | 31.2 | [5 empty] | stirrup | a | 8 | 1.2 | 1 | 2 | 13 | 31.2
| C-7 | Main Bar | 20 | 3.68 | 1 | 2 | 8 | 16 | [6 empty] | 58.88 | C-7 | Main Bar | 20 | 3.68 | 1 | 2 | 8
| Stirupe | a | 8 | 1.2 | 1 | 2 | 13 | 26 |  | 31.2 | [5 empty] | stirrup | a | 8 | 1.2 | 1 | 2 | 13 | 31.2
| C-8 | Main Bar | 20 | 3.68 | 1 | 2 | 8 | 16 | [6 empty] | 58.88 | C-8 | Main Bar | 20 | 3.68 | 1 | 2 | 8
| Stirupe | b | 8 | 1.3 | 1 | 2 | 13 | 26 |  | 33.8 | [5 empty] | stirrup | b | 8 | 1.3 | 1 | 2 | 13 | 33.8
| First Floor | [6 empty] | 0 | [7 empty] | First Floor
| C-1 | Main Bar | 20 | 3.68 | 1 | 2 | 12 | 24 | [6 empty] | 88.32 | C-1 | Main Bar | 20 | 3.68 | 1 | 2 | 12
| Stirupe | a | 8 | 1.2 | 1 | 2 | 13 | 26 |  | 31.2 | [5 empty] | Stirrup | a | 8 | 1.2 | 1 | 2 | 13 | 31.2
| C-2 | Main Bar | 20 | 3.68 | 1 | 2 | 8 | 16 | [6 empty] | 58.88 | C-2 | Main Bar | 20 | 3.68 | 1 | 2 | 8
| Stirupe | a | 8 | 1.2 | 1 | 2 | 13 | 26 |  | 31.2 | [5 empty] | Stirrup | a | 8 | 1.2 | 1 | 2 | 13 | 31.2
| C-3 | Main Bar | 20 | 3.68 | 1 | 2 | 12 | 24 | [6 empty] | 88.32 | C-3 | Main Bar | 20 | 3.68 | 1 | 2 | 12
| b | b | 8 | 1.2 | 1 | 2 | 13 | 26 |  | 31.2 | [5 empty] | a | a | 8 | 1.2 | 1 | 2 | 13 | 31.2
| C-4 | Main Bar | 16 | 3.52 | 1 | 10 | 8 | 80 | [5 empty] | 281.6 |  | C-4 | Main Bar | 16 | 3.52 | 1 | 10 | 8
| Stirupe | a | 8 | 1.2 | 1 | 10 | 14 | 140 |  | 168 | [5 empty] | Stirrup | a | 8 | 1.2 | 1 | 10 | 14 | 168
| C-5 | Main Bar | 20 | 3.68 | 1 | 2 | 8 | 16 | [6 empty] | 58.88 | C-5 | Main Bar | 20 | 3.68 | 1 | 2 | 8
| b | b | 8 | 1.2 | 1 | 2 | 13 | 26 |  | 31.2 | [5 empty] | a | a | 8 | 1.2 | 1 | 2 | 13 | 31.2
| C-6 | Main Bar | 16 | 3.52 | 1 | 2 | 8 | 16 | [5 empty] | 56.32 |  | C-6 | Main Bar | 16 | 3.52 | 1 | 2 | 8
| Stirupe | a | 8 | 1.2 | 1 | 2 | 14 | 28 |  | 33.6 | [5 empty] | Stirrup | a | 8 | 1.2 | 1 | 2 | 14 | 33.6
| C-7 | Main Bar | 16 | 3.52 | 1 | 2 | 8 | 16 | [5 empty] | 56.32 |  | C-7 | Main Bar | 16 | 3.52 | 1 | 2 | 8
| Stirupe | a | 8 | 1.2 | 1 | 2 | 14 | 28 |  | 33.6 | [5 empty] | Stirrup | a | 8 | 1.2 | 1 | 2 | 14 | 33.6
| C-8 | Main Bar | 20 | 3.68 | 1 | 2 | 8 | 16 | [6 empty] | 58.88 | C-8 | Main Bar | 20 | 3.68 | 1 | 2 | 8
| Stirupe | b | 8 | 1.3 | 1 | 2 | 13 | 26 |  | 33.8 | [5 empty] | Stirrup | a | 8 | 1.2 | 1 | 2 | 14 | 33.6
[8 empty] | 0 | [7 empty] | Second Floor
| Second Floor | [6 empty] | 0 | [7 empty] | C-1 | Main Bar | 16 | 3.52 | 1 | 2 | 12
| C-1 | Main Bar | 16 | 3.52 | 1 | 2 | 12 | 24 | [5 empty] | 84.48 |  | stirrup | a | 8 | 1.2 | 1 | 2 | 14 | 33.6
| Stirupe | a | 8 | 1.2 | 1 | 2 | 14 | 28 |  | 33.6 | [5 empty] | C-2 | Main Bar | 16 | 3.52 | 1 | 2 | 8
| C-2 | Main Bar | 16 | 3.52 | 1 | 2 | 8 | 16 | [5 empty] | 56.32 |  | stirrup | a | 8 | 1.2 | 1 | 2 | 14 | 33.6
| Stirupe | a | 8 | 1.2 | 1 | 2 | 14 | 28 |  | 33.6 | [5 empty] | C-3 | Main Bar | 20 | 3.68 | 1 | 2 | 8
| C-3 | Main Bar | 20 | 3.68 | 1 | 2 | 8 | 16 | [6 empty] | 58.88 | b | a | 8 | 1.2 | 1 | 2 | 13 | 31.2
| b | b | 8 | 1.2 | 1 | 2 | 13 | 26 |  | 31.2 | [5 empty] | C-4 | Main Bar | 14 | 3.44 | 1 | 10 | 8
| C-4 | Main Bar | 14 | 3.44 | 1 | 10 | 8 | 80 |  |  |  |  | 275.2 |  |  | stirrup | a | 8 | 1.2 | 1 | 10 | 16 | 192
| Stirupe | a | 8 | 1.2 | 1 | 10 | 16 | 160 |  | 192 | [5 empty] | C-5 | Main Bar | 16 | 3.52 | 1 | 2 | 8
| C-5 | Main Bar | 16 | 3.52 | 1 | 2 | 8 | 16 | [5 empty] | 56.32 |  | b | b | 8 | 1.2 | 1 | 2 | 14 | 33.6
| b | b | 8 | 1.2 | 1 | 2 | 14 | 28 |  | 33.6 | [5 empty] | C-6 | Main Bar | 16 | 3.52 | 1 | 2 | 8
| C-6 | Main Bar | 16 | 3.52 | 1 | 2 | 8 | 16 | [5 empty] | 56.32 |  | stirrup | a | 8 | 1.2 | 1 | 2 | 14 | 33.6
| Stirupe | a | 8 | 1.2 | 1 | 2 | 14 | 28 |  | 33.6 | [5 empty] | C-7 | Main Bar | 16 | 3.52 | 1 | 2 | 8
| C-7 | Main Bar | 16 | 3.52 | 1 | 2 | 8 | 16 | [5 empty] | 56.32 |  | stirrup | a | 8 | 1.2 | 1 | 2 | 14 | 33.6
| Stirupe | a | 8 | 1.2 | 1 | 2 | 14 | 28 |  | 33.6 | [5 empty] | C-8 | Main Bar | 16 | 3.52 | 1 | 2 | 8
| C-8 | Main Bar | 16 | 3.52 | 1 | 2 | 8 | 16 | [5 empty] | 56.32 |  | stirrup | a | 8 | 1.2 | 1 | 2 | 14 | 33.6
| Stirupe | b | 8 | 1.2 | 1 | 2 | 14 | 28 |  | 33.6 | [5 empty] | Third Floor
[8 empty] | 0 | [7 empty] | C-1 | Main Bar | 16 | 3.52 | 1 | 2 | 12
| Third Floor | [6 empty] | 0 | [7 empty] | stirrup | a | 8 | 1.2 | 1 | 2 | 14 | 33.6
| C-1 | Main Bar | 16 | 3.52 | 1 | 2 | 12 | 24 | [5 empty] | 84.48 |  | C-2 | Main Bar | 16 | 3.52 | 1 | 2 | 8
| Stirupe | a | 8 | 1.2 | 1 | 2 | 14 | 28 |  | 33.6 | [5 empty] | stirrup | a | 8 | 1.2 | 1 | 2 | 14 | 33.6
| C-2 | Main Bar | 16 | 3.52 | 1 | 2 | 8 | 16 | [5 empty] | 56.32 |  | C-3 | Main Bar | 16 | 3.52 | 1 | 2 | 8
| Stirupe | a | 8 | 1.2 | 1 | 2 | 14 | 28 |  | 33.6 | [5 empty] | b | b | 8 | 1.2 | 1 | 2 | 14 | 33.6
| C-3 | Main Bar | 16 | 3.52 | 1 | 2 | 8 | 16 | [5 empty] | 56.32 |  | C-4 | Main Bar | 14 | 3.44 | 1 | 10 | 8
| b | b | 8 | 1.2 | 1 | 2 | 14 | 28 |  | 33.6 | [5 empty] | stirrup | a | 8 | 1.2 | 1 | 10 | 16 | 192
| C-4 | Main Bar | 14 | 3.44 | 1 | 10 | 8 | 80 |  |  |  |  | 275.2 |  |  | C-5 | Main Bar | 16 | 3.52 | 1 | 2 | 8
| Stirupe | a | 8 | 1.2 | 1 | 10 | 16 | 160 |  | 192 | [5 empty] | b | b | 8 | 1.2 | 1 | 2 | 14 | 33.6
| C-5 | Main Bar | 16 | 3.52 | 1 | 2 | 8 | 16 | [5 empty] | 56.32 |  | C-6 | Main Bar | 14 | 3.44 | 1 | 2 | 8
| b | b | 8 | 1.2 | 1 | 2 | 14 | 28 |  | 33.6 | [5 empty] | stirrup | a | 8 | 1.2 | 1 | 2 | 16 | 38.4
| C-6 | Main Bar | 14 | 3.44 | 1 | 2 | 8 | 16 |  |  |  |  | 55.04 |  |  | C-7 | Main Bar | 14 | 3.44 | 1 | 2 | 8
| Stirupe | a | 8 | 1.2 | 1 | 2 | 16 | 32 |  | 38.4 | [5 empty] | stirrup | a | 8 | 1.2 | 1 | 2 | 16 | 38.4
| C-7 | Main Bar | 14 | 3.44 | 1 | 2 | 8 | 16 |  |  |  |  | 55.04 |  |  | C-8 | Main Bar | 16 | 3.52 | 1 | 2 | 8
| Stirupe | a | 8 | 1.2 | 1 | 2 | 16 | 32 |  | 38.4 | [5 empty] | stirrup | b | 8 | 1.2 | 1 | 2 | 14 | 33.6
| C-8 | Main Bar | 16 | 3.52 | 1 | 2 | 8 | 16 | [5 empty] | 56.32
| Stirupe | b | 8 | 1.2 | 1 | 2 | 14 | 28 |  | 33.6
| Fourth Floor | [6 empty] | 0 | [7 empty] | Fourth Floor
| C-1 | Main Bar | 16 | 3.21 | 1 | 2 | 8 | 16 | [5 empty] | 51.36 |  | C-1 | Main Bar | 16 | 3.21 | 1 | 2 | 8
| Stirupe | a | 8 | 1.2 | 1 | 2 | 15 | 30 |  | 36 | [5 empty] | stirrup | a | 8 | 1.2 | 1 | 2 | 15 | 36
| C-2 | Main Bar | 16 | 3.21 | 1 | 2 | 8 | 16 | [5 empty] | 51.36 |  | C-2 | Main Bar | 16 | 3.21 | 1 | 2 | 8
| Stirupe | a | 8 | 1.2 | 1 | 2 | 15 | 30 |  | 36 | [5 empty] | stirrup | a | 8 | 1.2 | 1 | 2 | 15 | 36
| C-3 | Main Bar | 16 | 3.21 | 1 | 2 | 8 | 16 | [5 empty] | 51.36 |  | C-3 | Main Bar | 16 | 3.21 | 1 | 2 | 8
| b | b | 8 | 1.2 | 1 | 2 | 15 | 30 |  | 36 | [5 empty] | b | b | 8 | 1.2 | 1 | 2 | 15 | 36
| C-4 | Main Bar | 14 | 3.21 | 1 | 10 | 8 | 80 |  |  |  |  | 256.8 |  |  | C-4 | Main Bar | 14 | 3.21 | 1 | 10 | 8
| Stirupe | a | 8 | 1.2 | 1 | 10 | 17 | 170 |  | 204 | [5 empty] | stirrup | a | 8 | 1.2 | 1 | 10 | 17 | 204
| C-5 | Main Bar | 16 | 3.21 | 1 | 2 | 8 | 16 | [5 empty] | 51.36 |  | C-5 | Main Bar | 16 | 3.21 | 1 | 2 | 8
| b | b | 8 | 1.2 | 1 | 2 | 15 | 30 |  | 36 | [5 empty] | b | b | 8 | 1.2 | 1 | 2 | 15 | 36
| C-6 | Main Bar | 14 | 3.21 | 1 | 2 | 8 | 16 |  |  |  |  | 51.36 |  |  | C-6 | Main Bar | 14 | 3.21 | 1 | 2 | 8
| Stirupe | a | 8 | 1.2 | 1 | 2 | 17 | 34 |  | 40.8 | [5 empty] | stirrup | a | 8 | 1.2 | 1 | 2 | 17 | 40.8
| C-7 | Main Bar | 14 | 3.21 | 1 | 2 | 8 | 16 |  |  |  |  | 51.36 |  |  | C-7 | Main Bar | 14 | 3.21 | 1 | 2 | 8
| Stirupe | a | 8 | 1.2 | 1 | 2 | 17 | 34 |  | 40.8 | [5 empty] | stirrup | a | 8 | 1.2 | 1 | 2 | 17 | 40.8
| C-8 | Main Bar | 16 | 3.21 | 1 | 2 | 8 | 16 | [5 empty] | 51.36 |  | C-8 | Main Bar | 16 | 3.21 | 1 | 2 | 8
| Stirupe | b | 8 | 1.2 | 1 | 2 | 15 | 30 |  | 36 | [5 empty] | stirrup | b | 8 | 1.2 | 1 | 2 | 15 | 36
[8 empty] | 0 | [7 empty] | stirrup | a | 8 | 1.2 | 1 | 2 | 17
| Floor Beam and Slab Mesh | [6 empty] | 0 | [7 empty] | C-8 | Main Bar | 16 | 3.21 | 1 | 2 | 8
| First - 4th Floor | [14 empty] | stirrup | b | 8 | 1.2 | 1 | 2 | 15 | 36
| On Axis A | Top Bar | 14 | 8.23 | 4 | 1 | 2 | 8 |  |  |  |  | 65.84
|  |  | 14 | 8.88 | 4 | 1 | 4 | 16 |  |  |  |  | 142.08
|  |  | 14 | 8.3 | 4 | 1 | 2 | 8 |  |  |  |  | 66.4
|  | Negative Bar | 14 | 3.36 | 4 | 1 | 2 | 8 |  |  |  |  | 26.88
|  | Bttm | 14 | 10.425 | 4 | 1 | 2 | 8 |  |  |  |  | 83.4
|  |  | 14 | 3.875 | 4 | 1 | 2 | 8 |  |  |  |  | 31
|  |  | 14 | 4.34 | 4 | 1 | 2 | 8 |  |  |  |  | 34.72
|  |  | 14 | 8.38 | 4 | 1 | 2 | 8 |  |  |  |  | 67.04 |  |  | On Axis A' & B'
|  |  | 14 | 10.575 | 4 | 1 | 2 | 8 |  |  |  |  | 84.6
|  | Stirrups | 8 | 1.26 | 4 | 1 | 160 | 640 |  | 806.4
| On Axis A' & B' | Top Bar | 14 | 6.74 | 4 | 2 | 2 | 16 |  |  |  |  | 107.84 |  |  | On Axis A0
|  | Bttm | 14 | 4.39 | 4 | 2 | 2 | 16 |  |  |  |  | 70.24
|  | Stirrups | 8 | 1.26 | 4 | 2 | 20 | 160 |  | 201.6
| On Axis A⁰ | Top Bar | 14 | 6.06 | 4 | 2 | 2 | 16 |  |  |  |  | 96.96
|  | Bttm | 14 | 5.4 | 4 | 2 | 2 | 16 |  |  |  |  | 86.4
|  | stirrup | 8 | 1.26 | 4 | 2 | 25 | 200 |  | 252
| On Axis C | Top Bar | 14 | 8.23 | 4 | 1 | 4 | 16 |  |  |  |  | 131.68 |  |  | On Axis C
|  |  | 14 | 8.88 | 4 | 1 | 4 | 16 |  |  |  |  | 142.08
|  | Negative Bar | 14 | 3.035 | 4 | 1 | 2 | 8 |  |  |  |  | 24.28
|  |  | 14 | 3.36 | 4 | 1 | 2 | 8 |  |  |  |  | 26.88
|  | Bttm | 14 | 10.425 | 4 | 1 | 4 | 16 |  |  |  |  | 166.8
|  |  | 14 | 3.53 | 4 | 1 | 2 | 8 |  |  |  |  | 28.24
|  |  | 14 | 4.34 | 4 | 1 | 2 | 8 |  |  |  |  | 34.72
|  |  | 14 | 8.38 | 4 | 1 | 2 | 8 |  |  |  |  | 67.04
|  | Stirrups | 8 | 1.26 | 4 | 1 | 160 | 640 |  | 806.4
| On Axis 1 & 8 | Top Bar | 16 | 10.21 | 4 | 2 | 2 | 16 | [5 empty] | 163.36
|  | Negative Bar | 16 | 3.005 | 4 | 2 | 3 | 24 | [5 empty] | 72.12 |  | On Axis 1 & 8
|  |  | 16 | 1.915 | 4 | 2 | 2 | 16 | [5 empty] | 30.64
|  |  | 14 | 4.025 | 4 | 2 | 2 | 16 |  |  |  |  | 64.4
|  | Bttm | 14 | 9.55 | 4 | 2 | 2 | 16 |  |  |  |  | 152.8
|  | Stirrups | 8 | 1.26 | 4 | 2 | 43 | 344 |  | 433.44
| On Axis 2 & 7 | Top Bar | 20 | 11.54 | 4 | 2 | 2 | 16 | [6 empty] | 184.64 | On Axis 2 & 7
|  | Negative Bar | 20 | 3.195 | 4 | 2 | 1 | 8 | [6 empty] | 25.56
|  |  | 20 | 1.915 | 4 | 2 | 3 | 24 | [6 empty] | 45.96
|  |  | 20 | 3.005 | 4 | 2 | 4 | 32 | [6 empty] | 96.16
|  | Bttm | 20 | 10.885 | 4 | 2 | 2 | 16 | [6 empty] | 174.16
|  |  | 20 | 4.025 | 4 | 2 | 2 | 16 | [6 empty] | 64.4
|  | Stirrups | 8 | 1.26 | 4 | 2 | 44 | 352 |  | 443.52
|  | Stirrups | 10 | 1.26 | 4 | 2 | 42 | 336 |  |  | 423.36 | [5 empty] | 453.6
| On Axis 3 & 6 | Top Bar | 20 | 11.54 | 4 | 2 | 2 | 16 | [6 empty] | 184.64 | On Axis 3 & 6
|  | Negative Bar | 16 | 3.195 | 4 | 2 | 1 | 8 | [5 empty] | 25.56
|  |  | 20 | 1.915 | 4 | 2 | 3 | 24 | [6 empty] | 45.96
|  |  | 20 | 3.005 | 4 | 2 | 3 | 24 | [6 empty] | 72.12
|  | Bttm | 16 | 10.88 | 4 | 2 | 2 | 16 | [5 empty] | 174.08
|  |  | 16 | 4.025 | 4 | 2 | 3 | 24 | [5 empty] | 96.6
|  | Stirrups | 8 | 1.26 | 4 | 2 | 41 | 328 |  | 413.28
|  | Stirrups | 10 | 1.26 | 4 | 2 | 34 | 272 |  |  | 342.72 | [5 empty] | 383.04
| On Axis 4 & 5 | Top Bar | 16 | 10.22 | 4 | 2 | 2 | 16 | [5 empty] | 163.52 |  | On Axis 4 & 5
|  | Negative Bar | 16 | 1.55 | 4 | 2 | 2 | 16 | [5 empty] | 24.8
|  |  | 16 | 3.005 | 4 | 2 | 3 | 24 | [5 empty] | 72.12
|  |  | 16 | 1.915 | 4 | 2 | 3 | 24 | [5 empty] | 45.96
|  | Bttm | 14 | 9.55 | 4 | 2 | 2 | 16 |  |  |  |  | 152.8
|  |  | 14 | 2.9 | 4 | 2 | 1 | 8 |  |  |  |  | 23.2
|  |  | 14 | 4.025 | 4 | 2 | 2 | 16 |  |  |  |  | 64.4
|  | Stirrups | 8 | 1.26 | 4 | 2 | 68 | 544 |  | 685.44 | [5 empty] | Toptie Beam
| Toptie Beam | [15 empty] | On Axis A⁰ |  | 14 | 5.7 | 1 | 2 | 2
| On Axis A⁰ |  | 14 | 5.7 | 1 | 2 | 2 | 4 |  |  |  |  | 22.8 |  |  | On Axis A⁰ | Top Bar | 14 | 5.7 | 1 | 2 | 2
|  |  | 12 | 5.4 | 1 | 2 | 2 | 4 |  |  |  | 21.6 |  |  |  |  | Bttm | 12 | 5.4 | 1 | 2 | 2 |  | 52.2
|  |  | 8 | 0.9 | 1 | 2 | 29 | 58 |  | 52.2 | [6 empty] | Stirrups | 8 | 0.9 | 1 | 2 | 30 | 54
| On Axis A b/n Axis 1-2 & 7-8 |  | 14 | 5.73 | 1 | 2 | 2 | 4 |  |  |  |  | 22.92 |  |  | On Axis A b/n Axis 1-2 & 7-8 | Top Bar | 14 | 5.73 | 1 | 2 | 2
|  |  | 12 | 5.33 | 1 | 2 | 2 | 4 |  |  |  | 21.32 |  |  |  |  | Bttm | 12 | 5.33 | 1 | 2 | 2 |  | 50.4
|  |  | 8 | 0.9 | 1 | 2 | 28 | 56 |  | 50.4 | [6 empty] | Stirrups | 8 | 0.9 | 1 | 2 | 28 | 50.4
| On Axis A b/n Axis 3 & 6 |  | 14 | 6.56 | 1 | 1 | 4 | 4 |  |  |  |  | 26.24 |  |  | On Axis A b/n Axis 3 & 6 | Top Bar | 14 | 6.56 | 1 | 1 | 4
|  |  | 12 | 8.43 | 1 | 1 | 2 | 2 |  |  |  | 16.86 |  |  |  |  | Bttm | 12 | 8.43 | 1 | 1 | 2
|  |  | 12 | 4.39 | 1 | 1 | 2 | 2 |  |  |  | 8.78 | [5 empty] | 12 | 4.39 | 1 | 1 | 2 |  | 59.4
|  |  | 8 | 0.9 | 1 | 1 | 66 | 66 |  | 59.4 | [6 empty] | Stirrups | 8 | 0.9 | 1 | 1 | 66 | 59.4
| On Axis A' b/n Axis 4-5 |  | 14 | 4.7 | 1 | 1 | 2 | 2 |  |  |  |  | 9.4 |  |  | On Axis A' b/n Axis 4-5 | Top Bar | 14 | 4.7 | 1 | 1 | 2
|  |  | 12 | 4.4 | 1 | 1 | 2 | 2 |  |  |  | 8.8 |  |  |  |  | Bttm | 12 | 4.4 | 1 | 1 | 2 |  | 20.7
|  |  | 8 | 0.9 | 1 | 1 | 23 | 23 |  | 20.7 | [6 empty] | Stirrups | 8 | 0.9 | 1 | 1 | 22 | 19.8
| On Axis B |  | 14 | 5.7 | 1 | 2 | 2 | 4 |  |  |  |  | 22.8 |  |  | On Axis B | Top Bar | 14 | 5.7 | 1 | 2 | 2
|  |  | 12 | 5.4 | 1 | 2 | 2 | 4 |  |  |  | 21.6 |  |  |  |  | Bttm | 12 | 5.4 | 1 | 2 | 2 |  | 50.4
|  |  | 8 | 0.9 | 1 | 2 | 28 | 56 |  | 50.4 | [6 empty] | Stirrups | 8 | 0.9 | 1 | 2 | 28 | 50.4
| On Axis C |  | 14 | 8.05 | 1 | 1 | 4 | 4 |  |  |  |  | 32.2 |  |  | On Axis C | Top Bar | 14 | 8.05 | 1 | 1 | 4
|  |  | 14 | 8.88 | 1 | 1 | 4 | 4 |  |  |  |  | 35.52 |  |  |  |  | 14 | 8.88 | 1 | 1 | 4
|  |  | 12 | 10.43 | 1 | 1 | 4 | 4 |  |  |  | 41.72 |  |  |  |  | Bttm | 12 | 10.43 | 1 | 1 | 4
|  |  | 14 | 8.38 | 1 | 1 | 2 | 2 |  |  |  |  | 16.76 |  |  |  |  | 14 | 8.38 | 1 | 1 | 2
|  |  | 12 | 4.34 | 1 | 1 | 2 | 2 |  |  |  | 8.68 | [5 empty] | 12 | 4.34 | 1 | 1 | 2 |  | 159.3
|  |  | 8 | 0.9 | 1 | 1 | 177 | 177 |  | 159.3 | [6 empty] | Stirrups | 8 | 0.9 | 1 | 1 | 177 | 159.3
| AXIS-1,4,5 & 8 |  | 14 | 9.85 | 1 | 4 | 2 | 8 |  |  |  |  | 78.8 |  |  | AXIS-1,4,5 & 8 | Top Bar | 14 | 9.85 | 1 | 4 | 2
|  |  | 12 | 9.55 | 1 | 4 | 2 | 8 |  |  |  | 76.4 |  |  |  |  | Bttm | 12 | 9.55 | 1 | 4 | 2 |  | 172.8
|  |  | 8 | 0.9 | 1 | 4 | 48 | 192 |  | 172.8 | [6 empty] | Stirrups | 8 | 0.9 | 1 | 4 | 48 | 172.8
| AXIS 2,3,6&7 |  | 14 | 11.4 | 1 | 4 | 2 | 8 |  |  |  |  | 91.2 |  |  | AXIS 2,3,6&7 | Top Bar | 14 | 11.4 | 1 | 4 | 2
|  |  | 14 | 3.1 | 1 | 4 | 2 | 8 |  |  |  |  | 24.8 |  |  |  | Bttm | 14 | 3.1 | 1 | 4 | 2
|  |  | 12 | 11.1 | 1 | 4 | 2 | 8 |  |  |  | 88.8 | [5 empty] | 12 | 11.1 | 1 | 4 | 2 |  | 201.6
|  |  | 8 | 0.9 | 1 | 4 | 56 | 224 |  | 201.6 | [6 empty] | Stirrups | 8 | 0.9 | 1 | 4 | 56 | 201.6
| AXIS-2⁰ & 6⁰ |  | 14 | 5.85 | 1 | 2 | 2 | 4 |  |  |  |  | 23.4 |  |  | AXIS-2⁰ & 6⁰ | Top Bar | 14 | 5.85 | 1 | 2 | 2
|  |  | 12 | 5.55 | 1 | 2 | 2 | 4 |  |  |  | 22.2 |  |  |  |  | Bttm | 12 | 5.55 | 1 | 2 | 2 |  | 52.2
|  |  | 8 | 0.9 | 1 | 2 | 29 | 58 |  | 52.2 | [6 empty] | Stirrups | 8 | 0.9 | 1 | 2 | 29 | 52.2
| On Axis B' | Top Bar | 14 | 9.74 | 1 | 2 | 2 | 4 |  |  |  |  | 38.96 |  |  | On Axis B' | Top Bar | 14 | 9.74 | 1 | 2 | 2
|  | Bttm | 12 | 9.44 | 1 | 2 | 2 | 4 |  |  |  | 37.76 |  |  |  |  | Bttm | 12 | 9.44 | 1 | 2 | 2 |  | 90
|  | Stirrups | 8 | 0.9 | 1 | 2 | 50 | 100 |  | 90 | [6 empty] | Stirrups | 8 | 0.9 | 1 | 2 | 53 | 95.4
| Precast Bracing |  | 12 | 2 | 4 | 1 | 32 | 128 |  |  |  | 256 |  |  |  | Precast Bracing | 32
|  |  | 14 | 3.38 | 4 | 1 | 84 | 336 |  |  |  |  | 1135.68 |  |  |  | 172.8
|  |  | 14 | 3.04 | 4 | 1 | 60 | 240 |  |  |  |  | 729.6
|  |  | 12 | 2.7 | 4 | 1 | 24 | 96 |  |  |  | 259.2
|  |  | 10 | 2 | 4 | 1 | 4 | 16 |  |  | 32
|  |  | 10 | 1.8 | 4 | 1 | 24 | 96 |  |  | 172.8
| Slab Mesh |  | 6 | 32.52 | 4 | 1 | 5 | 20 | 650.4 | [6 empty] | Slab Mesh
|  |  | 6 | 14.34 | 4 | 1 | 20 | 80 | 1147.2
|  |  | 6 | 5.22 | 4 | 1 | 4 | 16 | 83.52
|  |  | 6 | 9.4 | 4 | 1 | 62 | 248 | 2331.2
|  |  | 6 | 10.73 | 4 | 1 | 34 | 136 | 1459.28
|  |  | 6 | 5.31 | 4 | 1 | 14 | 56 | 297.36
|  |  | 8 | 3.84 | 4 | 1 | 3 | 12 |  | 46.08
| Stair | [6 empty] | 0 | [7 empty] | Stair
| First Flight | 1 | 12 | 1.33 | 1 | 1 | 10 | 10 |  |  |  | 13.3 |  |  |  | First Flight
|  | 2 | 12 | 1.88 | 1 | 1 | 10 | 10 |  |  |  | 18.8
|  | 3 | 12 | 4.505 | 1 | 1 | 10 | 10 |  |  |  | 45.05
|  | 5 | 12 | 1.5 | 1 | 1 | 10 | 10 |  |  |  | 15
|  | 4 | 12 | 2.13 | 1 | 1 | 10 | 10 |  |  |  | 21.3
|  | 6 | 8 | 0.895 | 1 | 9 | 6 | 54 |  | 48.33
|  |  | 8 | 1.3 | 1 | 1 | 36 | 36 |  | 46.8
|  |  | 8 | 3.79 | 1 | 1 | 10 | 10 |  | 37.9
|  |  | 8 | 1.5 | 1 | 1 | 7 | 7 |  | 10.5
|  |  | 12 | 1.5 | 1 | 1 | 9 | 9 |  |  |  | 13.5
| 2nd, 4th, 6th and 8th Flight | 8 | 12 | 2.35 | 4 | 1 | 10 | 40 |  |  |  | 94 |  |  |  | 2nd, 4th, 6th and 8th Flight
|  | 9 | 12 | 5.01 | 4 | 1 | 10 | 40 |  |  |  | 200.4
|  | 10 | 12 | 2.575 | 4 | 1 | 10 | 40 |  |  |  | 103
|  | 7 | 12 | 1.465 | 4 | 1 | 10 | 40 |  |  |  | 58.6
|  | 6 | 8 | 0.895 | 4 | 9 | 6 | 216 |  | 193.32
|  |  | 8 | 1.3 | 4 | 1 | 38 | 152 |  | 197.6
| 3rd, 5th and 7th Flight | 11 | 12 | 1.325 | 3 | 1 | 10 | 30 |  |  |  | 39.75 |  |  |  | 3rd, 5th and 7th Flight
|  | 12 | 12 | 1.72 | 3 | 1 | 10 | 30 |  |  |  | 51.6
|  | 13 | 12 | 5.46 | 3 | 1 | 10 | 30 |  |  |  | 163.8
|  | 5 | 12 | 1.5 | 3 | 1 | 10 | 30 |  |  |  | 45
|  | 4 | 12 | 2.13 | 3 | 1 | 10 | 30 |  |  |  | 63.9
|  | 6 | 8 | 0.895 | 3 | 9 | 6 | 162 |  | 144.99
|  |  | 8 | 1.3 | 3 | 1 | 38 | 114 |  | 148.2
|  |  | 8 | 3.79 | 3 | 1 | 10 | 30 |  | 113.7
|  |  | 8 | 1.5 | 3 | 1 | 7 | 21 |  | 31.5
|  |  | 12 | 1.5 | 3 | 1 | 9 | 27 |  |  |  | 40.5
| Landing Beam reinforcement |  | 14 | 4.94 | 4 | 1 | 2 | 8 |  |  |  |  | 39.52 |  |  | Landing Beam reinforcement
|  |  | 14 | 4.44 | 4 | 1 | 2 | 8 |  |  |  |  | 35.52
|  |  | 8 | 1.1 | 4 | 1 | 22 | 88 |  | 96.8
| Solid slab at Floor Levels |  | 12 | 1.05 | 4 | 1 | 9 | 36 |  |  |  | 37.8 |  |  |  | Landing slab reinforcement | 37.8
|  |  | 8 | 0.575 | 4 | 1 | 7 | 28 |  | 16.1
| Additional |  | 8 | 1.14 | 4 | 1 | 6 | 24 |  | 27.36 | [5 empty] | Additional
0
[6 empty] | Total Length |  |  | 5968.96 | 8225.46 | 970.88 | 1915.02 | 5448.84 | 2477.24 | 1776.8
[6 empty] | Unit Weight |  |  | 0.222 | 0.422 | 0.626 | 0.887 | 1.195 | 1.595 | 2.434
[6 empty] | Total Weight |  |  | 1325.11 | 3471.14 | 607.77 | 1698.62 | 6511.36 | 3951.2 | 4324.73 | 21889.93

## ceramic res. (hidden)
| Project: Low Cost Housing Development Project | [5 empty] | For All Bearing Capacity of E-1
| Location: Jemmo II | [5 empty] | Super-Structure
| Client: Nifasilk Lafto Sub-City |  |  |  |  | Pay №
Contractor:
| Consultant: MGM Consult PLC |  |  |  |  | Date:
Code | Timizing |  |  | Dimension | Qty | Item | Description
Ceramic area
Ground -4th floor
| 5 | 1 | 1 | 5.07 |  |  | @ Studio Type [ 1pc .]
|  |  |  | 1.5 |  |  | L=1.51*2+0.65+1.4
38.03
| 5 | 1 | 1 | 6.01 |  |  | @ Three bed rm Type [ 1pc .]
|  |  |  | 1.5 |  |  | L=2.09*2+1.29+0.54
45.08
| 5 | 1 | 2 | 5.37 |  |  | @ One bed rm Type [ 2pcs .] b/n axis 3 to 6
|  |  |  | 1.5 |  |  | L=0.66+1.65*2+1.41
80.55
| 5 | 1 | 1 | 6.35 |  |  | @ Two bed rm Type [ 1pcs .]
|  |  |  | 1.5 |  |  | L=0.7+2.1*2+1.45
47.63
| 5 | 1 | 1 | 5.17 |  |  | @ One bed rm Type [ 2pcs .] b/n axis 7 to 8
|  |  |  | 1.5 |  |  | L=1.5*2+0.66+1.41+0.05*2
38.78
F7.1.5 |  |  |  |  | 250.07 |  | Total to Item 7.1.5
[6 empty] | 7.1.7 | 15×15×0.6cm white glazed ceramic wall tile for toilet
Ditto as item 7.1.5
Total to 7.1.7
[6 empty] | 7.1.8 | 330x30mm terrazzo thread bedded and joined with cement mortar 1:3 mix.
Ground to fourth floor
| 1 | 8 | 9 | 1.35
[5 empty] | 97.2 |  | Total to 7.1.8
[6 empty] | 7.1.9 | 160x30mm terrazzo riser bedded and joined with cement mortar 1:3 mix.
Ground to fourth floor
| 1 | 8 | 9 | 1.35
[5 empty] | 97.2 |  | Total to 7.1.9
[6 empty] | 7.1.10 | 28x3cm terrazzo window sill bedded and joined with cement mortar 1:3 mix. | -1 | 1 | 6 | 1.5 |  | W-1
[7 empty] | Ground to fourth floor |  |  |  | 1.5
| 5 | 1 | 1 | 28.4 | [7 empty] | -13.5
[5 empty] | 142 |  | Total to 7.1.10 | -1 | 1 | 9 | 1.2 |  | W-2
1.5
-16.2
[8 empty] | -1 | 1 | 5 | 1 |  | W-3
1.5
-7.5
[8 empty] | -1 | 1 | 6 | 0.6 |  | W-4
0.6
-2.16